A

SYNOPSIS REPORT

On

AI-Powered Job Application Agent

(Automated Job Search, Resume Tailoring and Application System)

Submitted as part of Work Based Learning Internship

at

National Institute of Electronics and Information Technology (NIELIT), Tezpur

Submitted by

KRISHNAMONI DAS

Under the guidance of

Shri. Bimal Goswami

May, 2026

# Table of Contents

| 1 | Project Introduction | 1 |
| --- | --- | --- |
| 2 | Objectives | 2 |
| 3 | Features | 3 |
| 4 | Theoretical Background | 4 |
| 5 | Problem Definition | 5 |
| 6 | Proposed Technology Stack | 5 |
| 7 | Software Requirements Specification (SRS) Document | 6 |
| 8 | Hardware Requirements | 8 |
| 9 | Development Methodology (Waterfall) | 9 |
| 10 | PERT Chart | 12 |
| 11 | Gantt Chart | 13 |
| 12 | Conclusion | 13 |

# 1. Project Introduction

The AI-Powered Job Application Agent is an intelligent automation system designed to help job seekers — particularly students and fresh graduates — streamline the tedious process of job hunting. The system automatically finds relevant job listings, tailors the candidate's resume to match each job description, generates personalised cover letters, and sends applications via email, all without manual intervention.

In today's highly competitive job market, applying for multiple positions requires significant time and effort. Each company expects a resume customised to its specific requirements and keywords. Manually tailoring dozens of applications is both time-consuming and prone to oversight. This project addresses that problem by leveraging Large Language Models (LLMs), web scraping, and automation to handle the entire application pipeline.

The system is built entirely using free and open-source tools — making it accessible to students with no budget. It uses the Groq API (free LLM inference), Playwright for headless web scraping, pdfplumber for resume parsing, ReportLab for PDF generation, Gmail SMTP for email delivery, SQLite for job tracking, and Streamlit for a visual dashboard.

This project demonstrates practical applications of Artificial Intelligence, Natural Language Processing, and software automation — making it highly relevant for the current industry landscape.

# 2. Objectives

The primary objectives of this project are:

- To automatically scrape job listings from multiple portals (Internshala, Indeed, Naukri) based on the user's target role and location.

- To analyse each job description using an LLM and extract required skills, keywords, and role summary.

- To score the candidate's resume against each job description and filter out poor matches.

- To tailor the candidate's resume per job using AI — reordering bullet points, injecting relevant keywords, and strengthening action verbs — without fabricating any information.

- To generate a personalised cover letter for each company automatically.

- To export the tailored resume to a PDF file for each application.

- To send the application (resume + cover letter) via Gmail SMTP to the candidate's email for review.

- To maintain a local SQLite database tracking job status: found, tailored, and applied.

- To provide a Streamlit dashboard to visualise job matches, download tailored resumes, and monitor application progress.

- To make the entire system available at zero cost using only free-tier tools and open-source libraries.

# 3. Features

## 3.1 Multi-Source Job Scraping

The agent simultaneously scrapes job listings from three major portals — Internshala (ideal for freshers), Indeed India, and Naukri.com — using Playwright headless browser automation. All results are combined and deduplicated.

## 3.2 AI-Powered JD Analysis

Each job description is analysed by the Groq LLM (Llama 3.3 70B) to extract structured data including required skills, preferred skills, ATS keywords, role summary, and experience requirements.

## 3.3 Resume Match Scoring

The system scores the candidate's resume against each job's requirements on a scale of 0 to 100. Jobs below a configurable threshold (default: 40) are automatically skipped, saving API calls and focusing effort on suitable matches.

## 3.4 AI Resume Tailoring

The LLM rewrites the resume to highlight the most relevant experience first, inject job-specific keywords for ATS compatibility, and strengthen action verbs — strictly using only information already present in the original resume. No fabrication occurs.

## 3.5 Personalised Cover Letter Generation

A tailored, human-sounding cover letter is generated per company, referencing the specific role and incorporating matching achievements from the resume.

## 3.6 PDF Export

The tailored resume is exported as a professional PDF using the ReportLab library, named per company and role for easy organisation.

## 3.7 Gmail Email Sending

Applications are sent to the candidate's own Gmail address for review via Gmail SMTP using an App Password. No third-party email service or paid API is required.

## 3.8 SQLite Job Tracker

Every job found, its match score, status, and application timestamps are stored in a local SQLite database that persists across runs.

## 3.9 Streamlit Dashboard

A web-based dashboard at localhost:8501 provides metrics (total found, tailored, applied), filterable job table, cover letter previews, downloadable PDFs, and a match score distribution chart.

# 4. Theoretical Background

## 4.1 Large Language Models (LLMs)

Large Language Models are deep learning models trained on massive text corpora to understand and generate human language. This project uses Llama 3.3 70B via the Groq API. The model performs natural language understanding (extracting structured data from JDs), natural language generation (writing cover letters and tailored resume content), and JSON-structured output for downstream processing.

## 4.2 Web Scraping

Web scraping is the automated extraction of data from websites. Playwright is a headless browser framework that renders JavaScript-heavy pages, allowing the agent to interact with modern job portals that do not expose public APIs. BeautifulSoup is used to parse the rendered HTML.

## 4.3 Applicant Tracking Systems (ATS)

Most companies use ATS software to filter resumes before human review. ATS systems rank resumes based on keyword density and match with the job description. This project uses LLMs to inject the most relevant ATS keywords from each job description into the tailored resume, improving shortlisting probability.

## 4.4 Prompt Engineering

Prompt engineering is the practice of crafting inputs to LLMs that consistently produce the desired output format and quality. This project uses structured prompts with explicit constraints (e.g., 'return only valid JSON', 'never fabricate facts') to ensure reliable, parseable outputs.

## 4.5 SQLite and Persistent State

SQLite is a serverless relational database embedded in Python's standard library. It stores job application state across multiple agent runs, enabling incremental processing and preventing duplicate applications.

# 5. Problem Definition

Job seeking is one of the most repetitive and time-consuming activities for students and graduates. The core problems addressed by this project are:

- Manual searching across multiple job portals is inefficient and misses many listings.

- Customising a resume for each company is time-consuming but critical for ATS compatibility.

- Writing unique cover letters for every application is tedious and often leads to generic, ineffective letters.

- Tracking which jobs have been applied to, and with which resume version, is difficult without a system.

- Students often cannot afford paid tools like LinkedIn Premium or resume optimisation services.

This project solves all of the above with a single, free, automated pipeline that runs with one command.

# 6. Proposed Technology Stack

| Component | Tool / Library | Cost |
| --- | --- | --- |
| LLM / AI | Groq API (Llama 3.3 70B) | Free tier |
| Web Scraping | Playwright + BeautifulSoup4 | Free / Open source |
| Resume Parsing | pdfplumber | Free / Open source |
| PDF Export | ReportLab | Free / Open source |
| Email Sending | Gmail SMTP (App Password) | Free |
| Database | SQLite (Python built-in) | Free |
| Dashboard UI | Streamlit | Free |
| Programming Language | Python 3.10+ | Free |
| Version Control | Git + GitHub | Free |

# 7. Software Requirements Specification (SRS)

## 7.1 Functional Requirements

- FR1: The system shall scrape job listings from at least three portals based on configurable role and location inputs.

- FR2: The system shall extract structured data (skills, keywords, summary) from each job description using an LLM.

- FR3: The system shall compute a numerical match score (0–100) between the user resume and each job description.

- FR4: The system shall tailor the resume for jobs with a match score above the configurable threshold (default: 40).

- FR5: The system shall generate a unique cover letter for each qualifying job.

- FR6: The system shall export each tailored resume to a PDF file.

- FR7: The system shall send the tailored resume and cover letter to the user's email via Gmail SMTP.

- FR8: The system shall persist job status in a local SQLite database.

- FR9: The system shall provide a Streamlit dashboard displaying all tracked jobs and allowing PDF download.

## 7.2 Non-Functional Requirements

- NFR1: The system shall complete the full pipeline for 5 jobs in under 10 minutes on a standard laptop.

- NFR2: The system shall never fabricate or hallucinate information in tailored resumes.

- NFR3: All data (resume, API keys) shall remain on the user's local machine.

- NFR4: The system shall operate using only free and open-source tools with no mandatory paid subscriptions.

- NFR5: The system shall handle scraping failures gracefully and continue processing remaining jobs.

- NFR6: The system shall be cross-platform (Windows, macOS, Linux).

## 7.3 Input Requirements

- User's resume (PDF or TXT format)

- Target role and location (configured in agent.py)

- Groq API key and Gmail App Password (stored in .env file)

## 7.4 Output Requirements

- Tailored resume PDF per qualifying job (saved to output/ folder)

- Cover letter text file per qualifying job

- Email sent to user's Gmail with attached resume

- Updated SQLite database with job status

- Streamlit dashboard at localhost:8501

# 8. Hardware Requirements

| Component | Minimum | Recommended |
| --- | --- | --- |
| Processor | Intel Core i3 / AMD Ryzen 3 | Intel Core i5 or higher |
| RAM | 4 GB | 8 GB or higher |
| Storage | 2 GB free space | 10 GB SSD |
| Internet | Required (for scraping + Groq API) | Broadband 10 Mbps+ |
| Operating System | Windows 10 / Ubuntu 20.04 | Windows 11 / Ubuntu 22.04 / macOS |
| Browser Engine | Chromium (via Playwright) | Chromium (auto-installed) |

# 9. Development Methodology (Waterfall)

This project follows the Waterfall Model of software development — a sequential, phase-driven approach where each phase must be completed before the next begins. The Waterfall model is suitable for this project because the requirements are well-defined upfront, the scope is bounded, and the deliverables at each phase are clear.

## Phase 1: Requirements Analysis

Duration: Week 1

- Identify the problem: manual, repetitive job application process

- Define system scope: job scraping, resume tailoring, email sending, dashboard

- Identify free tools and APIs available for each component

- Define functional and non-functional requirements (SRS)

- Deliverable: Approved SRS Document

## Phase 2: System Design

Duration: Week 2

- Design the overall system architecture and data flow pipeline

- Design the database schema (jobs and applications tables)

- Design the module structure (tools/ folder with llm.py, scraper.py, resume.py, emailer.py, database.py)

- Design prompt templates for JD analysis, resume tailoring, and cover letter generation

- Deliverable: Architecture diagram and module design document

## Phase 3: Implementation

Duration: Weeks 3–5

- Week 3: Implement scraper.py (Playwright scraping for Internshala, Indeed, Naukri)

- Week 3: Implement database.py (SQLite schema, CRUD operations)

- Week 4: Implement llm.py (Groq API wrapper), resume.py (parse, score, tailor, export)

- Week 4: Implement emailer.py (Gmail SMTP)

- Week 5: Implement agent.py (main orchestrator connecting all modules)

- Week 5: Implement dashboard.py (Streamlit UI)

- Deliverable: Complete working codebase

## Phase 4: Testing

Duration: Week 6

- Unit testing: test each module independently (scraper, LLM, resume parser, emailer)

- Integration testing: run full pipeline end-to-end with sample resume and real job listings

- Edge case testing: handle scraping failures, LLM JSON parse errors, empty resume

- Performance testing: measure time for 5-job pipeline on minimum hardware

- Deliverable: Test report with pass/fail results

## Phase 5: Deployment

Duration: Week 7

- Package project as a ZIP with setup instructions

- Write comprehensive README.md with step-by-step setup guide

- Verify setup on a clean Python environment

- Deliverable: Final deployable project package

## Phase 6: Maintenance

Duration: Week 8

- Monitor for website layout changes that may break scrapers

- Update scraper selectors as needed

- Add support for additional job portals

- Deliverable: Updated codebase with bug fixes

# 10. PERT Chart

The PERT (Program Evaluation and Review Technique) chart below shows the task dependencies and critical path for the project:

| Task | Activity | Duration | Depends On | Type |
| --- | --- | --- | --- | --- |
| T1 | Requirements gathering and SRS | 1 week | - | Critical |
| T2 | System and module design | 1 week | T1 | Critical |
| T3 | Web scraper development | 1 week | T2 | Critical |
| T4 | Database setup | 3 days | T2 | Parallel |
| T5 | LLM integration (Groq API) | 4 days | T2 | Critical |
| T6 | Resume parser and tailoring | 4 days | T5 | Critical |
| T7 | PDF export and email module | 3 days | T4, T6 | Parallel |
| T8 | Main agent orchestrator | 3 days | T3, T6, T7 | Critical |
| T9 | Streamlit dashboard | 3 days | T8 | Parallel |
| T10 | Testing and bug fixes | 1 week | T8, T9 | Critical |
| T11 | Documentation and packaging | 3 days | T10 | Critical |

Critical Path: T1 → T2 → T3 → T5 → T6 → T8 → T10 → T11 (Total: ~7 weeks)

# 11. Gantt Chart

The Gantt chart below shows the week-wise schedule across the 8-week project duration:

| Activity | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Requirements & SRS | ██ |  |  |  |  |  |  |  |
| System Design |  | ██ |  |  |  |  |  |  |
| Web Scraper Development |  |  | ██ |  |  |  |  |  |
| Database Setup |  |  | ██ |  |  |  |  |  |
| LLM Integration |  |  |  | ██ |  |  |  |  |
| Resume Module |  |  |  | ██ | ██ |  |  |  |
| Email + PDF Module |  |  |  |  | ██ |  |  |  |
| Agent Orchestrator |  |  |  |  | ██ |  |  |  |
| Streamlit Dashboard |  |  |  |  | ██ |  |  |  |
| Testing & Bug Fixes |  |  |  |  |  | ██ |  |  |
| Documentation & Packaging |  |  |  |  |  |  | ██ |  |
| Review & Submission |  |  |  |  |  |  |  | ██ |

# 12. Conclusion

The AI-Powered Job Application Agent addresses a real and significant pain point faced by students and fresh graduates — the time-consuming, repetitive process of applying for jobs. By combining web scraping, large language models, PDF processing, and email automation into a single pipeline, the system demonstrates how AI can be used practically to solve everyday problems.

The project is particularly relevant because it is built entirely using free and open-source tools, making it accessible to any student regardless of financial constraints. It showcases skills in Python programming, REST API integration, natural language processing, database management, and frontend development with Streamlit.

From a learning perspective, this internship project covers a wide range of computer science concepts: web automation, prompt engineering, LLM integration, document processing, SMTP protocols, SQLite, and data visualisation. It is both a practical tool and a comprehensive learning exercise undertaken during the internship at NIELIT Tezpur.

Future enhancements could include adding support for more job portals (Wellfound, Freshersworld), implementing interview tracking, adding WhatsApp notifications, and deploying the system as a scheduled task that runs daily without user intervention.

In conclusion, this project represents a well-scoped, fully functional AI application that is deployable at zero cost, demonstrates industry-relevant technical skills, and provides genuine value to its users.

End of Synopsis Report